## Sheet1
Defect ID | Defect Description | Steps to Reproduce | Actual Result | Expected Result | Severity | Priority | Raised By | Defect Raised Date | Assigned To | Root Cause | Fix Applied | Status
D‑01 | Error occurring in role‑based POV (User/Admin/Supervisor) | Login with different roles and access restricted modules | Some roles can access unauthorized screens | Only permitted screens should be accessible per role | High | High |  | 05‑Apr |  | Missing role validation checks in controller layer | Role checks implemented at controller/service level | Closed
D‑02 | Payment is processed as pre‑paid instead of post‑paid | Book parking slot and proceed to payment immediately | System allows payment before parking usage | Payment should be allowed only after parking completion | High | High |  | 05‑Apr |  | Incorrect payment workflow design | Payment flow updated to post‑paid logic | Closed
D‑03 | Multiple passes can be activated simultaneously | Purchase monthly pass twice before expiry | Multiple active passes allowed | Only one active pass should exist at a time | Medium | High |  | 06‑Apr |  | Missing active‑pass validation | Validation added to restrict multiple active passes | Closed
D‑04 | My Bookings tab shows empty Status & Actions fields | Navigate to My Bookings page | Status & action buttons not displayed | Booking status and actions should be visible | Medium | Medium |  | 06‑Apr |  | UI binding issue in Angular component | UI bindings corrected | Closed
D‑05 | Mobile view navigation bar not accessible | Open application in mobile view | Navigation menu not responsive | Navigation should be accessible on all devices | Low | Medium |  | 06‑Apr |  | CSS responsiveness issue | Responsive layout fixes applied | Closed
D‑06 | Penalty not added to payable amount | Overstay parking duration | Only warning shown, no penalty added | Penalty must be included in total payable amount | High | High |  | 07‑Apr |  | Missing penalty calculation integration | Penalty calculation linked to payment module | Closed
D‑07 | Monthly report not generated | Select monthly report and generate | No report displayed | Monthly report should generate correctly | Medium | Medium |  | 07‑Apr |  | Date filter logic incorrect | Date range logic fixed | Closed
D‑08 | Recent booking history not shown in reports | Make a recent booking and view report | Latest booking missing | Reports should include recent bookings | Medium | Medium |  | 07‑Apr |  | Query sorting/filter issue | Updated query to fetch latest records | Closed