## Sheet1
n | Review Date | Deliverable Reviewed | Required Findings | Actual Findings | Resolution | Sign off
QL‑01 | 31‑Mar | Project Overview | Clear scope, objectives, and actors defined | Scope and actors clearly documented | No changes required | Scrum Master
QL‑02 | 02‑Apr | Product Backlog | All features mapped to business benefits | Feature list aligned with system goals | Approved | Scrum Master
QL‑03 | 03‑Apr | User Story Case Study | Complete functional coverage with business rules | Minor wording inconsistencies found | User stories refined and updated | Scrum Master
QL‑04 | 04‑Apr | Sprint Backlog | Task‑level breakdown with effort estimates | Initial effort mismatch identified | Backlog updated with accurate estimates (118 hrs) | Scrum Master
QL‑05 | 05‑Apr | Role‑Based Access Implementation | Access restricted per role (User/Admin/Supervisor) | Some role access overlap detected | Role checks corrected in code | Scrum Master
QL‑06 | 06‑Apr | Booking & Payment Flow | Payment should be post‑paid | Payment initially pre‑paid | Payment logic corrected | Scrum Master
QL‑07 | 07‑Apr | Penalty Calculation | Penalty must be added to payable amount | Only warning shown | Penalty integration completed | Scrum Master
QL‑08 | 08‑Apr | Reports Module | Monthly reports with latest bookings | Recent bookings missing | Query logic updated | Scrum Master
QL‑09 | 08‑Apr | Non‑Functional Requirements | Must align with actual implementation | JWT/Spring Security reference identified | NFR corrected to role‑based access | Scrum Master
QL‑10 | 09‑Apr | UI & Responsiveness | Screens must work across devices | Mobile navigation issue found | UI responsiveness fixed | Scrum Master
QL‑11 | 09‑Apr | Codebase Document | Clear architecture and structure explained | Documentation complete and accurate | Approved | Scrum Master
QL‑12 | 10‑Apr | Final Demo Readiness | End‑to‑end flow works without errors | All major flows validated | Approved for Final Review