## Sprint Backlog
Story | Sprint Backlog Item | Task | Volunteer | Task Details | Initial Effort Estimate (hrs) | Day 1 Remaining (hrs) | Day 2 Remaining (hrs) | Day 3 Remaining (hrs) | Day 4 Remaining (hrs) | Day 5 Remaining (hrs) | Day 6 Remaining (hrs) | Day 7 Remaining (hrs) | Day 8 Remaining (hrs) | Status
US01 | User Registration | Create Registration API |  | User creation with validations | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | Done
US02 | User Login | Login API & Session |  | Login, role check, session handling | 6 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | Done
US20 | Role Auth | Role-Based Access |  | Controller role enforcement | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Done
US03 | Vehicle Management | Add Vehicle API |  | Map vehicle to user | 5 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | Done
US04 | Slot Discovery | Fetch Slots API |  | Real-time availability | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | Done
US10 | Slot Admin | Add Slot (Admin) |  | Admin slot creation UI & API | 5 | 0 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | Done
US11 | Slot Admin | Update Slot Status |  | Enable/Disable slot | 4 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | Done
US05 | Booking | Book Slot |  | Slot locking + booking ID | 9 | 0 | 0 | 0 | 6 | 3 | 0 | 0 | 0 | Done
US06 | Booking | Cancel Booking |  | Slot unlock + logs | 4 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | Done
US16 | Serial Control | Serial Generation |  | Unique serial per booking | 4 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | Done
US07 | Payment | Payment API |  | Mock payment handling | 6 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 1 | Done
US08 | Invoice | Generate Invoice |  | PDF invoice generation | 4 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | Done
US13 | Alerts | Expiry Alert |  | 10-min scheduler | 4 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | Done
US15 | Exit | Validate Exit |  | Serial + payment validation | 7 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | Done
US14 | Penalty | Apply Penalty |  | Grace + percent logic | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | Done
US25 | Pass & Discount | Parking Pass |  | Weekly/Monthly passes | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | Done
US12 | Reports | Generate Reports |  | Admin reports & export | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | Done
US22 | Validation | UI Validation |  | Angular form validations | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Done
US23 | Stability | Exception Handler |  | Global exception handler | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Done
US09 | Booking History | View History API |  | Fetch paginated booking history | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Done
US17 | User Data Mgmt | User Entity Design |  | DB schema & constraints | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Done
US18 | Slot Data Mgmt | Slot Entity Design |  | Slot DB schema with enum | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Done
US19 | Booking Data Mgmt | Booking Entity |  | Booking DB relations | 5 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | Done
US21 | API Security | Token Validation |  | Token validation per request | 5 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | Done
US24 | Form Validation | Angular Form Validation |  | Pattern & mandatory checks | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Done
| Inital estimation trend |  |  |  | 123 | 15 | 17 | 17 | 16 | 18 | 12 | 23 | 5
| Actual estiamation trend |  |  |  | 108 | 15 | 17 | 12 | 11 | 13 | 12 | 23 | 5

## burntdown_chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8
123 | 108 | 91 | 74 | 58 | 40 | 28 | 5 | 0
108 | 93 | 76 | 64 | 55 | 40 | 28 | 5 | 0